## Arizona State Retirement System
Arizona State Retirement System - Dental (PPO) - January 1, 2021
Dental Implementation Critical Milestone Report
Last Updated on: 12/18/2019 |  |  |  | Overall Health: | On Schedule
# | Milestone | Product(s) Impacted | Significance | Target Completion Date | Status | Completion Date | Task Owner
1 | Customer Kick Off Meeting | Dental | Introduce team, identify contacts and begin implementation tasks. | 2020-03-25 | On Schedule |  | Arizona State Retirement System / MetLife
2 | Establish and Execute Meeting Schedule | Dental | Review and update tasks and deliverables for all parties involved in the implementation. Address any questions or concerns. | 2020-03-25 | On Schedule |  | Arizona State Retirement System / MetLife
3 | Banking | Dental | Determine whether it is wire or DTC. Need authorization from customer to open bank account and then provide banking screen to Plan Master in order for plans to be activated (in production) by Effective date. Plan Master can not activate plans without proof of bank account. | 2020-03-31 | On Schedule |  | Arizona State Retirement System / MetLife
4 | Determine Employee Communication Strategy | Dental | Determine if Customer will create their own employee communications to announce change in carrier to MetLife or if MetLife materials will be leveraged. This is necessary to avoid service or legal concerns. | 2020-04-06 | On Schedule |  | Arizona State Retirement System / MetLife
5 | Submit Application / Statement of Responsibility to Customer for Review | Dental | Application and Statement of Responsibility drafted by Contract Analyst and sent to the customer for review. | 2020-04-14 | On Schedule |  | MetLife
6 | Submit Administrative Services Agreement(s) to Customer for Review | Dental | Administrative Services Agreement(s) drafted, submitted to customer for review. Necessary for claims administration (appeals, litigations, etc). | 2020-04-20 | On Schedule |  | MetLife
7 | Reporting | Dental | Determine Customer needs of what MetLife will be providing to the customer in terms of reporting and analysis. | 2020-04-20 | On Schedule |  | Arizona State Retirement System / MetLife
8 | Receive Signed Customer Application / Statement of Responsibility | Dental | Application and Statement of Responsibility signed by the customer and returned to MetLife. | 2020-05-11 | On Schedule |  | MetLife
9 | Final Review / Approval of Administrative Services Agreement (ASA) | Dental | Customer provides final, signed copy of the Administrative Services Agreement(s). This is required for claims administration (appeals, litigations, etc.) | 2020-06-24 | On Schedule |  | Arizona State Retirement System
10 | Review and Finalize Plan Designs, Structure and Rates | Dental | Review, document and finalize the plan design, structure and rates via the Product, Rate, Services Summary (PRSS). This is needed to begin MetLife system setup. If there is an eligibility file, structure must be provided to the customer/TPA prior to the first test file being prepared and sent to MetLife. | 2020-07-17 | On Schedule |  | Arizona State Retirement System / MetLife
11 | Review and Finalize Performance Guarantees | Dental | Review and finalize Performance Guarantees. Applicable to all coverages in which Performance Guarantees were sold. | 2020-07-27 | On Schedule |  | Arizona State Retirement System / MetLife
12 | Eligibility File Setup | Dental | Determine mapping, transmission (PGP), connectivity and data elements and whether it is changes only or full population. | 2020-07-31 | On Schedule |  | Arizona State Retirement System / MetLife
13 | Provide First Eligibility Test File | Dental | TPA/Customer provides a production file. Necessary to have most accurate claims information for claims administration. | 2020-09-08 | On Schedule |  | Arizona State Retirement System / Third Party Administrator
14 | Customer Solutions Center (CSC) Operational | Dental | Customer Solutions Center (CSC) operational in order to service Employees | 2020-09-08 | On Schedule |  | MetLife
15 | SPD | Dental | Customer provides updated SPD's to MetLife for claims processing. | 2020-09-17 | On Schedule |  | Arizona State Retirement System
16 | Submit Fully Insured Policy / Certificate(s) to Customer for Review | Dental | Fully Insured Policy drafted, Fully Insured certificates drafted, submitted to customer for review. Necessary for claims administration (appeals, litigations, etc.) | 2020-10-05 | On Schedule |  | MetLife
17 | MetLife System Setup | Dental | MetLife production systems are updated based upon Plan Design, Structure and established intake and communication methods. | 2020-10-07 | On Schedule |  | MetLife
18 | Provide Second Eligibility Test File | Dental | TPA/Customer provides a production file. Necessary to have most accurate claims information for claims administration. | 2020-10-12 | On Schedule |  | Arizona State Retirement System / Third Party Administrator
19 | MetLink Set Up | Dental | Submit MetLife user request form, Set up users via MetLink admin tool, distribute temp ids/passwords. This allows customer access to claim and benefit information and reporting information. | 2020-10-23 | On Schedule |  | MetLife
20 | MyBenefits Set Up | Dental | Submit MetLife user request form, Set up users via MyBenefits admin tool, announce MyBenefits "go live". This allows employee access to claim and absence information and reporting information. | 2020-10-26 | On Schedule |  | MetLife
21 | Customer Training | Dental | Determine customer training needs, including MetLink and MyBenefits Training. MetLife facilitates training for customer. | 2020-10-27 | On Schedule |  | Arizona State Retirement System / MetLife
22 | Receive Final, Clean Test Eligibility File | Dental | TPA/Customer sends final, clean test file to MetLife. Necessary to confirm successful transmission of file, system acceptance of data elements and to confirm data element mapping is correct. | 2020-11-09 | On Schedule |  | MetLife
23 | Final Review / Approval of Fully Insured Policy / Certificates | Dental | Customer provides final sign off on Fully Insured policy and certificate(s). This is required for claims administration (appeals, litigations, etc.) | 2020-11-12 | On Schedule |  | Arizona State Retirement System
24 | Receive First Production Eligibility File | Dental | Necessary to have most accurate claims information for claims administration. | 2020-12-02 | On Schedule |  | MetLife
25 | Pre-Implementation Audit | Dental | TPA audit of MetLife claim process, if applicable | 2020-12-10 | On Schedule |  | Arizona State Retirement System / MetLife
26 | MetLife begins processing Dental Claims | Dental | MetLife begins processing Dental Claims | 2021-01-01 | On Schedule |  | MetLife
Legend
Green = On schedule
Yellow = Issues exist; Behind plan; Milestone not completed on schedule; If issues are not resolved, project end date will be risk
Red = Major issues exist; Project end date at risk
Blue = Milestone completed

## Internal Escalation (hidden)
Arizona State Retirement System - Dental (PPO) - January 1, 2021
Escalation Tracking Report
Document Owner Name | [5 empty] | FOR INSTRUCTION ONLY
Original Escaltion Date - MM/DD/YYYY | [5 empty] | When the Mood Status has changed from Green to Yellow or Red, please complete this tab. Once completed, copy and paste this tab and distribute via email to those on your escalation distribution.
Date Customer notified of status change: MM/DD/YYYY
Distribution email to:
CSC, FC, CSD, AE, IL Mngr, PL Mngr, PM Mngr, Contracts Mngr, Life Services Mngr, LRK Mngr, Life Services IL, Core IL
What Happened:
Example: The PRSS sign off date by the customer was missed, impacting the ability to load downstream systems approve structure (Highlight milestones that have been impacted as a result of this) | [5 empty] | Key Drivers for Escalation:
1- PRSS Missed target completion (impacts downstream GLIF, ATLAS, Website, Billing (CBS))
Why did it happen:
Example: The customer canceled meeting and discovered they need additional internal partners to review proposed structure provided by MetLife. There is no ETA on when they can complete this. | [5 empty] | 2- Eligibility (Define the population)
3 - Eligibility Test Files
How can we fix this: | [5 empty] | 4 - Participation Files
Example: Must obtain PRSS sign off within 5 business days and compress Contract and iLink QA to recover and go back to green status | [5 empty] | 5 - Bill & Remit Files
Next Steps:
Example: CSC to hold meeting with customer to obtain sign off on PRSS by the new target date needed to reach effective date on NOS. Management please review "How can we fix this" and prepare to compress durations / identify alternate solutions where possible.
Example of items extracted from Milestones and Project Schedule:
|  |  | Current Mood Date | MM/DD/YYYY
|  |  | Overall Health: | Select Response
# | Milestone | Product(s) Impacted | Significance | Target Resolution Date | Comments
1 | Send Final Plan Design and Structure to MetLife Contacts/Customer | Life | PRSS Signed off on and Complete | 2018-02-01
2 | Complete Life I-Link booklets | Life | iLink Completed by Amy | 2018-02-05
3 | Send e-mail to the QA Team | Life | iLink goes to QA | 2018-02-06
4 | Provide QA feedback via the QUAD database for CAC Review and Updates | Life | iLink QA come back after 3 days | 2018-02-09
5 | Draft Certificates/Policy/PG Agreement, if applicable | Life | Drafts start on 2/9 and finish 5 days later. | 2018-02-16 | Policy and PG's will need to lag so focus can be on Drafting Certs only.
6 | Provide Draft Certificates to QA Team | Life | Certs must go to QA | 2018-02-16 | We need support from QA to compress turnaround time to 1-2 business days please
7 | Confirm Initial Eligibility Test File is Received | LRK | Test Eligibility file MUST be received by TPA | 2018-02-19 | This may be a challenge for the TPA and the Account Executive is alerting the Customer a slip in this date will impact the install.
8 | Feed I-Link and provide link to Final PRSS document(s) to Plan Master | Life | Feed iLink | 2018-02-20
9 | Provide Contract Documents to Plan Master | Life | Requires fast edits from contracts and handoff to Plan Master | 2018-02-20
10 | Complete GLIF Audit | LRK | GLIF Audit | 2018-03-02
11 | Plan Master Activities | Life | 9 days beginning 2/20 and ends with plans in production on 3/5 | 2018-03-05 | Includes plan design review, cert review, resolve discrepancies in iLink / PRSS
12 | Receive and Load Production Eligibility File and Participant/Grandfathered File to UIS Train | LRK | Production file | 2018-03-09
13 | CBS Bill and Remit Testing | LRK | Runs 15 days from 3/29-4/18 | 2018-04-18
14 | Provide First Payroll Deduction File to Customer and notify Life Services Implementation Leader | LRK | Bill file to customer | 2018-05-08 | Bill file does not need to go to the customer until 5/8
Legend
Green = On schedule
Yellow = Issues exist; Behind plan; Incomplete Milestone
Red = Major issues exist; Project end date at risk
Blue = Milestone completed